AEGIS PROJECT REPORT

Chapter 4

Project Timeline

Htun Khaing Lynn  |  Student ID: 001557481

Aegis: API Security and Management System

# 4.1 DSDM Delivery Approach

The Project Proposal selected Agile DSDM because it combines fixed timeboxes, incremental delivery, MoSCoW prioritisation and regular review. This chapter applies the tutor feedback to make the plan a DSDM timebox plan only: it starts with design work rather than separate research, analysis or planning phases; activities are multi-day; and the final testing date is 9 October 2026. Research and analysis inform the work but are not presented as standalone timeline phases.

Each timebox includes a short foundation/checkpoint, development, test, review and retrospective activity. The work is ordered so that the Control Plane policy model is available before the proxy enforces it, and the POC and end-to-end tests follow a usable full-stack path.

# 4.2 Timebox Schedule

| Timebox | Dates | Primary focus | Multi-day outputs |
| --- | --- | --- | --- |
| TB1 | 16–27 Mar | Architecture and data-model design | Component boundaries, initial schema, key workflows |
| TB2 | 30 Mar–10 Apr | Security and interface design | API contract, authentication and enforcement sequence |
| TB3 | 13–24 Apr | Control Plane foundation | Async FastAPI, migrations, user/auth foundations |
| TB4 | 27 Apr–8 May | Identity and API-key delivery | RBAC, key issue/revoke, ownership controls |
| TB5 | 11–22 May | Policy configuration | Rate-limit and JWT configuration workflows |
| TB6 | 25 May–5 Jun | Proxy core | Go forwarding, internal key validation and cache |
| TB7 | 8–19 Jun | Traffic enforcement | Redis limits, JWT validation and response contracts |
| TB8 | 22 Jun–3 Jul | Policy distribution | REST snapshot, gRPC stream and resilience checks |
| TB9 | 6–17 Jul | Security controls | Threat rules, manual/automatic IP blocking |
| TB10 | 20–31 Jul | Observability | Sanitised events, analytics and dashboard integration |
| TB11 | 3–14 Aug | Route authorisation | Exact route-permission policy and scope enforcement |
| TB12 | 17–28 Aug | Integration hardening | Docker Compose, policy refresh and regression fixes |
| TB13 | 31 Aug–11 Sep | System test timebox | Component, integration and coverage checks |
| TB14 | 14–25 Sep | POC and acceptance timebox | Attack console, user-path checks and defect correction |
| TB15 | 28 Sep–9 Oct | Final test and report timebox | Regression, evaluation, documentation and submission preparation |

# 4.3 Timebox Controls

At the start of each timebox, confirm the MoSCoW scope and dependencies; do not move unfinished optional features ahead of an unverified security baseline.

During development, maintain small increments that can be tested at the Control Plane, proxy and dashboard boundaries.

At the end, run relevant automated tests, review acceptance evidence, record defects and use the retrospective to adjust the following timebox.

Treat quality as non-negotiable: a feature is not complete merely because it has a screen or endpoint; it needs an enforcement and test path where applicable.

# 4.4 Milestones and Dependencies

The critical chain is policy model → authenticated Control Plane API → proxy policy retrieval → enforcement → cross-component testing. The analytics and dashboard work depends on the proxy reporting an event safely, but it must not delay the security decision itself. The final two timeboxes are deliberately reserved for evidence-led testing and documentation, rather than adding a new functional phase outside the DSDM structure.

# References

Agile Business Consortium (2014) The DSDM Agile Project Framework. Tunbridge Wells: Agile Business Consortium.